## Sheet1
Space Wars Assets | Priority | Anibrain Status | [5 empty] | Nagarro Status
|  | Artist | Start Dtae | Completion Date | Status | Size | Remarks | Received | Integrated | Need Tweaking | Remarks
Mockups
Desktop | 0 | Mohit | 03.01.2017 | 12.01.2017 | Done
Touch-Land scape | 0 | Mohit | 13.01.2017 | 17.01.2017 | Done
Touch-Portrait | 0 | Mohit | 18.01.2017 | 24.01.2017 | Done
Main game
Game background with reel area | 1 | Mohit | 13.01.2017 | 14.01.2017 | Done
Game logo | 1 | Mohit | 13.01.2017 | 14.01.2017 | Done
Main game measurements (coordinate) | 1 | Mohit | 16.01.2017 | 18.01.2017 | Done
Portrait background(touch) | 3 | Mohit | 18.01.2017 | 24.01.2017 | Done
Symbols and animation
Basic Symbols | 1 | Mohit | 13.01.2017 | 14.01.2017 | Done
Blured Symbols | 1 | Mohit | 13.01.2017 | 14.01.2017 | Done
Low and medium symbols animation sprite | 2 | Mohit | 25.01.2017 | 03.02.2017 | Done
Wild symbol animation sprite | 2 | Mohit | 08.02.2017 | 09.02.2017 | Done
Keypad
Keypad buttons | 1 | Mohit | 13.01.2017 | 18.01.2017 | Done
keypad glow animation | 1 | Mohit | 13.01.2017 | 18.01.2017 | Done
Coin bars sprite/mockup | 1 | Mohit | 07.02.2017 | 08.02.2017 | Done
Betline
Betline indicator | 2 | Mohit | 30.01.2017 | 31.01.2017 | Done
Betline holder (lines/animation) | 3 | Mohit | 23.03.2017 | IN PROCESS | IN PROCESS
Betline color | 3 | Mohit | 30.01.2017 | 31.01.2017 | Done
Win Animation
Pod Animation in Basic game | 2 | Mohit | 09.02.2017 | 13.02.2017 | Done
Pod Animation with Symbols filling | 2 | Mohit | 14.02.2017 | 01.03.2017 | Done
Intro Screen
intro movie | 4 | Mohit | 01.02.2017 | 02.02.2017 | Done
splash screen | 4 | Mohit | 16.03.2017 | 17.03.2017 | Done
Win banner
win banner | 3 | Mohit | 07.02.2017 | 07.02.2017 | Done
win indicator number | 3 | Mohit | 15.02.2017 | 15.02.2017 | Done
Respin animation
re-spin light animation | 2 | Mohit | 16.03.2017 | 16.03.2017 | Done
Big win animation
big win banner | 4 | Mohit | 17.03.2017 | 23.03.2017 | Done
big win name font style | 4 | Mohit | NYS
big win video | 4 | Mohit | NYS
Paytable
paytable mockup image | 5 | Mohit | 10.03.2017 | 16.03.2017 | Done
paytable images | 5 | Mohit | 10.03.2018 | 16.03.2018 | Done
paytable button (on reel) | 5 | Mohit | 10.03.2019 | 16.03.2019 | Done
paytable button ( back next ) | 5 | Mohit | 10.03.2020 | 16.03.2020 | Done
Game Rule
Game Rule mockup | 6 | Mohit | 16.02.2017 | 16.02.2017 | Done